## Defect_reports
FIELD
Defect Identifier | DI_001 | DI_002 | DI_003 | DI_004
Defect Summary | Expected Result : when filtering products based on the price (max $40) , it is also showing products with higher price Actual Result: should only show products with price(actual + delivery) according to filtered condition | Expected Result: when user clicks Shop by category, it should diplay the a list of all the cateogies and it should be perfectly scrollable. Actual Result: all cateogories are displayed, but cannot properly scroll the category list | Expected Result: User’s country/language preference should persist across sessions (after logout/login) , Actual Result: Country resets to United States after logout/login, even though it was changed to Korea. | Expected Result: There should be an option to change language(country) in the mobile devices too , Actual result: There is no option for that in mobile devices
Test Id | TC_SR_04 | TC_AC_02 | TC_LC_10 | TC_LC_08
Test case name | Price Filter | Validate categories list loads and scroll | Verify preference saved in user profile | Verify language change on mobile
Module name | Search&Filter | All_Category | Country(Language) | Country(Language)
Reproducible | Yes | Yes | Yes | Yes
Severity | Medium(impacts user experience) | Medium(affects usability, but not effecting core function) | High (user personalization is lost) | High(blocks non-English users from using site on mobile)
Priority | High(sorting is a key function) | Medium(should be fixed soon as it effect user experience) | Medium - High (not a crash, but critical for user experience) | High (mobile is critical platform for users, should be fixed urgently)
Raised by | Raniya(Tester) | Raniya(Tester) | Raniya(Tester) | Raniya(Tester)
Assigned To | Team Lead | UI developer/Team Lead | Team Lead | UI developer/Team Lead
Date of assignment | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18
Status | Open | Open | Open | Open
Snap shot
Fixed by | - | - | - | -
Date of fixing | - | - | - | -
Approvals | QA Lead / Project manager | QA Lead / Project manager | QA Lead / Project manager | QA Lead / Project manager