## User Login
Section | Details
Project Name | E_Bay
Module Name | User Login
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Raniya
Date | 2025-08-18
1. Test Summary
Metric | Count
Total Test Cases | 10
Executed Test Cases | 10
Passed Test Cases | 9
Failed Test Cases | 1
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 9 | 90%
Failed | 1 | 10%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 1
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available): 100%
✅ Business Scenario Coverage: 0%
5. Observations
All core functional and security test cases passed except session timeout.
Session expiry not working - Users remain logged in indefinitely.
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Session not expiring after 30 mins idle time | Medium | Open
7. Recommendations
Implement session timeout handling (auto logout after 30 mins inactivity).

## Search&Filter
Section | Details
Project Name | E_Bay
Module Name | Search&Filter
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Raniya
Date | 2025-08-18
1. Test Summary
Metric | Count
Total Test Cases | 10
Executed Test Cases | 10
Passed Test Cases | 9
Failed Test Cases | 1
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 9 | 90%
Failed | 1 | 10%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 1
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available): 100%
✅ Business Scenario Coverage: 100%
5. Observations
Search and filter functionalities are working as expected for most flows.
Price filter issue observed - results are not strictly filtered by the selected range (some items outside 1000–5000 appeared).
Auto-suggest, pagination, category filter, and sorting all function as expected.
Performance test (response < 2s) passed consistently.
Risk/Issue Description | Impact | Status | Comments
Price filter not working properly | High | Open | Impacts user trust, may show irrelevant results.
Search works for blank input (shows all categories) | Low | Open | Usability concern; might cause unnecessary server load.
7. Recommendations
Fix price filter logic to ensure results are strictly within the applied range.
Improve blank search handling - instead of showing all results, show a message like “Please enter a keyword”.

## Cart
Section | Details
Project Name | E_Bay
Module Name | Cart
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Raniya
Date | 2025-08-19
1. Test Summary
Metric | Count
Total Test Cases | 9
Executed Test Cases | 9
Passed Test Cases | 9
Failed Test Cases | 0
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 9
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 9 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available):100%
✅ Business Scenario Coverage: 100%
5. Observations
All Cart module functionalities are working as expected.
Cart updates (add, remove, quantity change, price calculation) are consistent.
Coupon application and invalid coupon handling are functioning correctly.
Risk/Issue Description | Impact | Status | Comments
User experience can be improved by showing confirmation messages for actions like “Save for later” or “Remove item” | low
7. Recommendations
Maintain automation for all cart operations to ensure regression safety.
Optionally, enhance UI feedback for user actions (like quantity update, item removal)

## Profile Managemnet
Section | Details
Project Name | E_Bay
Module Name | Profile Update
Release Version | v1.2.3
SDLC Methodology | Agile (Sprint 1)
Prepared By | Raniya
Date | 2025-08-19
1. Test Summary
Metric | Count
Total Test Cases | 10
Executed Test Cases | 10
Passed Test Cases | 9
Failed Test Cases | 1
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 9 | 90%
Failed | 1 | 10%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available): 100%
✅ Business Scenario Coverage: 100%
5. Observations
Profile Update module is mostly stable, allowing users to update name and address.
Validation for invalid characters in address failed in one scenario (TC_PU_06).
Manual testing and automation results are consistent.
Max length, blank field, cancel operations, and combined updates are handled correctly.
Risk/Issue Description | Impact | Status | Comments
Invalid characters accepted in address field | Medium | Open | Could allow malicious input or affect downstream modules
7. Recommendations
Fix address validation logic to reject invalid symbols.
Maintain automation for all profile update test cases to ensure regression coverage.
Optional: Enhance input validation messaging to be more user-friendly.

## All_Category
Section | Details
Project Name | E_Bay
Module Name | Shop by All Categories
Release Version | v1.2.3
SDLC Methodology | Agile (Sprint 1)
Prepared By | Raniya
Date | 2025-08-19
1. Test Summary
Metric | Count
Total Test Cases | 9
Executed Test Cases | 9
Passed Test Cases | 7
Failed Test Cases | 2
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 9
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 7 | 77%
Failed | 2 | 23%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 2
Critical Defects | 0
High Severity Defects | 1
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available):100%
✅ Business Scenario Coverage: 100%
5. Observations
Most functionalities are working as expected: categories visible, clickable, sub-categories listed, search works, mobile responsiveness is fine.
Scrolling issue in categories list reduces usability.
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Categories list not scrollable properly | Medium | Open | User may not be able to view all categories easily.
7. Recommendations
Fix scrolling issue to ensure all categories are visible and accessible

## Specific_Category
Section | Details
Project Name | E_Bay
Module Name | Shop by Specific Category
Release Version | v1.2.3
SDLC Methodology | Agile (Sprint 1)
Prepared By | Raniya
Date | 2025-08-19
1. Test Summary
Metric | Count
Total Test Cases | 10
Executed Test Cases | 10
Passed Test Cases | 9
Failed Test Cases | 1
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 9 | 90%
Failed | 1 | 10%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 1
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available):100%
5. Observations
Navigation to categories, sub-categories, add to cart, pagination, empty categories, and responsiveness work as expected.
Sorting functionality is not working correctly, which affects usability and product discovery.
Performance for category load time is acceptable (<3 sec).
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Sorting not working correctly | Medium | Open | Users cannot view products in proper order.
7. Recommendations
Fix sorting functionality to ensure products are displayed in correct order

## Product Details
Section | Details
Project Name | E_Bay
Module Name | Product Details Page
Release Version | v1.2.3
SDLC Methodology | Agile (Sprint 1)
Prepared By | Raniya
Date | 2025-08-19
1. Test Summary
Metric | Count
Total Test Cases | 10
Executed Test Cases | 10
Passed Test Cases | 9
Failed Test Cases | 1
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 9 | 90%
Failed | 1 | 10%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 1
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available):100%
5. Observations
Product information, price, images, description, and Add to Cart/Buy Now buttons work correctly.
Product page load time and mobile responsiveness are acceptable.
Out of stock handling is implemented correctly.
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
Maintain automation coverage for all functional, usability, performance, and security test cases.

## Country(Language)
Section | Details
Project Name | E_Bay
Module Name | Country(Language)
Release Version | v1.2.3
SDLC Methodology | Agile (Sprint 1)
Prepared By | Raniya
Date | 2025-08-19
1. Test Summary
Metric | Count
Total Test Cases | 9
Executed Test Cases | 9
Passed Test Cases | 6
Failed Test Cases | 3
Blocked Test Cases | 0
Not Executed Test Cases | 0
Automation Covered | Yes
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 6 | 66%
Failed | 3 | 33%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 3
Critical Defects | 1
High Severity Defects | 2
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 100%
✅ Code Coverage (if available):100%
5. Observations
Dropdown and basic language switching work as expected on desktop.
Confirmation message missing reduces clarity for users.
Mobile option missing affects usability on mobile devices.
Preference persistence issue is a critical concern for user experience.
Currency updates correctly when country changes
Risk/Issue Description | Impact | Status | Comments
Confirmation message missing | Medium | Open | Users may not know if the update succeeded.
Language change not available on mobile | High | Open | Mobile users cannot switch language.
Preference not saved after logout/login | Critical | Open | Serious impact on user personalization and experience.
7. Recommendations
Implement confirmation message after language/country change.
Ensure mobile support for language/country switching.
Fix user preference persistence issue to save changes across sessions